## project
Project Plan
Team Members | [7 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Daniel Canfield | s1511832
Glenn Curran | s1506145
TBC | numbers
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | STAGE | HOUR
LECTURE | ACTIVITY | START | DURATION | START | DURATION | COMPLETE | CONTRIBUTORS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Software Development Life Cycle | Gantt Chart Plan | 1 | 1 | 1 | 1 | 100% | DC
Software Development Life Cycle | Assignment Flowchart | 2 | 3 | 2 | 3 | 100% | DC, GC
Software Development Life Cycle | Pseudocode | 3 | 1 | TBA | TBA | 0%
Software Development Life Cycle | Pseudocode Actualization | 4 | 1 | TBA | TBA | 0%
Software Development Methodology | Pair Programming | 5 | 1 | TBA | TBA | 0%
Software Development Methodology | Pair Programming Testing | 6 | 1 | TBA | TBA | 0%
Versioning | Bitbucket - Initialization | 7 | 1 | TBA | TBA | 0%
Versioning | Bitbucket - Pull Code | 8 | 1 | TBA | TBA | 0%
Versioning | Bitbucket - Push Code | 9 | 1 | TBA | TBA | 0%
Versioning | Bitbucket - Branch Code | 10 | 1 | TBA | TBA | 0%
Versioning | Bitbucket - Label Code | 11 | 1 | TBA | TBA | 0%
Finite-State Machines | Development on Paper | 12 | 1 | TBA | TBA | 0%
Project Management | SCRUM Team - Creation | 13 | 1 | TBA | TBA | 0%
Project Management | SCRUM Team - Dummy Sprint | 14 | 1 | TBA | TBA | 0%
Programming Data Structures | Tree Data Structure - Design and Implementation | 15 | 1 | TBA | TBA | 0%
Programming Data Structures | Tree Data Structure - Algorithm Creation | 16 | 1 | TBA | TBA | 0%
Programming Classes | Class Creation | 17 | 1 | TBA | TBA | 0%